2nd Avenue Subway Construction Look Ahead

March 15Th 2011 to April 4th  2011

| location | description of work |
| --- | --- |
| 100th to 99th Streets | Set up Rebar Fabrication Yard. Con Edison pulling & splicing cables. |
| 99th to 97th Streets | Verizon: Pull cable and splice at 97th St. (7pm-7am). Breakout and relocate existing cables south of 98th. Cap Existing 30” Gas at Metropolitan hospital |
| 97th to 96th Streets | Install secant piles at north/west wall of Ancillary 2. Excavate and Deck for watermain at intersection. Install 36” watermain and backfill when complete To...; 2nd ave subway email list.. |
| 96th to 95th Streets | Excavate and Deck for Water main center of 96th. Excavate and install 16” house connection for 1849 2nd Avenue Excavate and install 35” watermain heading south. |
| 95th to 94th Streets | Revise traffic pattern to allow traffic on the East side of 2nd Ave and establish work zone on West side of 2nd Ave. |
| 94th to 93rd Streets | Interior demolition of Rainbow Hardware (Entrance One) Installation of cellar ties at 1814 2nd Ave. |
| 93rd to 92nd Street | Mucking operations suspended until further notice. |
| 92nd to 91st Streets | Tunnel Boring Machine completed west tunnel. Reposition & reassemble TBM for east tunnel run. TBM currently in Launch Box at 92nd Street. Scheduled to beginning east side Tunnel Boring 1st week of April 2011 |
| 91st to 90th Streets | Continuing ground freezing. |
| 87th to 86th Streets | Work zone located on West side of 2nd Ave. Installation and tie in of new 12” water line. New hydrant connections. Completion of Con Ed Duct work. |
| 86th to 85th Streets | Maintenance and Protection of Traffic - Contractor material storage area 12” water main & Con Electric |
| 85th to 84th Streets | Maintenance and Protection of Traffic - Contractor material storage area |
| 84th to 83rd Streets | West Side: Continue support of excavation installation. Mechanical excavation of rock. DOT permit for closure of 83rd St between 1st & 2nd and between 2nd & 3rd Aves between 9am and 5pm Monday thru Friday. Continue with electric conduit & man hole installations. Con Ed cable/splicing |
| 83rd to 82nd Streets | Maintenance and Protection of Traffic- Contractor material storage area. Con Edison cable splicing |
| 79th to 78th Streets | Center Maintenance and Protection of Traffic |
| 74th to 73rd Streets | Operation of dewatering tanks. |
| 73rd to 72nd Streets | Continuing controlled blasting activities on 2nd Avenue. |
| 72nd Street North West Side | Continuing interior demolition of 259 E 72nd St Ancillary 2. Installation of Support of Excavation walls on East face. Gas and electrical utility relocation |
| 72nd to 71st Streets | Contractor storage and maintenance area |
| 71st to 70th Streets | Connecting utilities for employee work trailers |
| 70th to 69th Street | Continuing of controlled blasting activities on 2nd Avenue. Installation of instrumentation to 63rd Street |
| 69th Street North West Side | Gas and electrical utility relocations. Preparation for Asbestos abatement. |
| 3rd Ave between 62nd and 63rd Street | Relocation of M 102,103,104 bus stop to 65th Street. Installation of Geo-tech instrumentation. |

SAS WORK HOURS:

MONDAY - FRIDAY, 7:00 AM TO 10:00 PM

SATURDAY, 10:00 AM TO 7:00 PM

WORK UNDER DECKING PERMITTED 24 HOURS

BE ADVISED:  Con Ed, Empire City Subway and Verizon may be performing cable and gas line work outside regular SAS construction Hours.  If you have additional questions, please contact Claudia Wilson at (212) 792-9716 from 9:00AM to 5:00PM Monday through Friday, or contact the 2nd Avenue Subway Hotline 24 hours/7 days a week at (646)252-2670.

TRAFFIC UPDATES

100th to 95th Streets

- Four lanes of traffic on the East side of Second Avenue

- Work zone will be set up on the West side of Second Ave

- The West side work zone will be approximately 40 Foot wide, plus 7 Foot sidewalk

- No Standing at Anytime on the West side of Second Ave 95th Street to 101st Street

- No Standing on the East side 7AM-10AM and 4PM-7PM Monday-Friday

- No Standing on East side 10AM-4PM, EXCEPT Trucks Loading and Unloading

95th Street to 91St Streets

- Four lanes of traffic currently on  WEST Side of 2nd Avenue

- Work zone is set up on the EAST SIDE of 2nd Avenue

- The EAST SIDE work zone will be approximately 40 FOOT wide, plus 7' sidewalk

- No Standing at anytime on the EAST SIDE of Second Ave 91st Street to 96th Street

- No Standing on the WEST SIDE 7AM-10AM and 4PM-7PM Monday-Friday except truck loading or unloading

- Parking ALLOWED on WEST SIDE 7PM-7AM Weekdays and all day Saturday

87th to 82nd Streets

- From 88th Street to 86th Street Traffic lanes East and West of Center Work Zone

- From 85th Street to 82nd Street Three lanes of traffic on the East Side of Second Ave

- Work zone will be set up on the West Side of Second Ave South of 85th St

- The West Side work zone will be approximately 40 Foot wide, plus 7 Foot sidewalk

- No Standing at Anytime on the East Side of Second Ave 87th Street to 82nd Street

- No Standing at Anytime on the West Side of Second Avenue 87th to 86th Street, EXCEPT Trucks Loading and Unloading

- No Standing on East or West Side 85th to 82nd Streets (NYPD Traffic enforced)

74th to 68th Streets

- Work zone is set up on the EAST SIDE of Second Ave

- The EAST SIDE work zone will be approximately 40 FOOT wide, plus 7’sidewalk

- No Standing at anytime on the EAST  SIDE of Second Ave

- No Standing on the WEST  SIDE 7AM-10AM and 4PM-7PM Monday-Friday

- No Standing on WEST SIDE 10 AM-4PM, EXCEPT trucks loading and unloading

- Parking ALLOWED on WEST SIDE 7PM-7AM Weekdays and all day Saturday & Sunday